## 2024-27 Action Plan
HREiR Action plan template (2024-2027)
Details
|  | Institution name: | Leeds Beckett University |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
|  | Cohort number: | 12 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
|  | Date of submission: | 2024-02-23 |  |  |  | Research staff |  | 210 | Defined as having the job titles: Research Assistant, Research Officer, (Postdoc) Research Fellow, Senior Research Fellow, Reader, Professor and Director of Research
|  | Institutional context: | The University employs just over 2800 academic and professional services staff based across 8 multidisciplinary academic schools and central services. The main beneficiaries of the Concordat Action Plan are those whose primary responsibility is to conduct research. This group, referred to in this plan as research staff, includes research assistants, research officers, research fellows (both senior and postdoc), readers, professors, and Directors of Research. The University recognises the crucial role our research staff play in advancing our research and teaching goals. This commitment to research is captured in our 2021-26 Strategic Framework objective: "To be recognised globally as an outstanding university generating research of impact and significance". This sentiment is further echoed in the Research & Innovation aim: "We are all engaged in growing high-quality research, innovation, and knowledge exchange and feel supported to fulfil our potential". |  |  |  | Research and Teaching Staff |  | 865 | Of whom a portion will be research active and thereby beneficiaries of this action plan
[7 empty] | Post Graduate Researchers |  | 663 | Portions of these groups will benefit from the action plan below but are not within the cohort on which progress will be monitored.
[7 empty] | Professional support staff |  | 1422
[7 empty] | Clinicians |  | 0
[7 empty] | Technicians |  | 0
Other (please provide numbers and details):
| Complete for submission | [7 empty] | To be completed only when reporting on action plan
|  | Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure a broad understanding and awareness of this amongst researchers. LBU is dedicated to enhancing the research environment through a series of targeted actions designed to respond to specific feedback from CEDARS and the wider university community. This feedback has highlighted a need for greater acknowledgment of researchers' contributions to policymaking and an enhancement of our inclusive research culture. Through these initiatives, we aim to foster a research community where every member feels valued and is empowered to contribute to our collective research endeavours.
| ECI1 | Ensure all relevant staff are aware of the Concordat. | Focus will be intensified on leveraging the Concordat to enhance professional and career development frameworks. Priority actions include a comprehensive review and update of the PDR resources for the 2024 cycle, specifically tailored to research staff needs. This update will incorporate direct references to the Concordat, building upon existing practices in select schools where it already underpins development programmes. The aim is to more distinctly embed the Concordat's principles within professional development and career advancement structures, ensuring they are explicitly recognised and utilised in shaping researcher pathways. | yes (ECI1) | Ongoing | The Academy | Ongoing improvement in awareness of the Concordat and HREiR will be measured through staff surveys (e.g., CEDARS), click rates on blogs, newsletter articles, and other relevant publicity. CEDARS: 60% of respondents who are research only or have more than 61% of their time allocated to research will indicate they have some understanding of The Concordat to Support the Career Development of Researchers. Annual focus groups to take place in 2025, and 2026 to evaluate the effectiveness of awareness raising activities related to The Concordat. The first session in 2025 will establish a baseline, with the expectation that awareness will increase in subsequent years.
| ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Building upon our existing annual policy review, we are set to concentrate on several key areas: Comprehensive Communication Strategy: We will develop and implement a targeted communication strategy to enhance awareness of our institutional policies and practices. This strategy will employ a variety of channels, including email newsletters, the university website, and social media, to effectively reach our beneficiaries. It will feature updates on policies, provide insights into policy development, and share stories that underscore the practical application and impact of these policies. | yes (ECI2) | Autumn 2024 | RIG | Increased awareness of institutional policies among researchers and managers, as measured by engagement metrics. Achieve a 15% increase in digital interactions related to institutional policies in year 1, evidenced by metrics such as website policy page views, document downloads, newsletter click-through rates, and social media engagement (likes, shares, comments) on policy-related posts. Target for remaining years will be a 10% increase year on year.
|  |  | Policy Awareness Workshops and Training Sessions: Organise annual workshops or training sessions for researchers and managers that focus on understanding and effectively implementing institutional policies. These sessions may be tailored to address different career stages and roles. | Yes (ECI2) | 2025-07-03 | RIG | Workshop feedback: Over 90% positive feedback will be received in terms of clarity, relevance, and practical applicability of the content, based on standardised post-session evaluation forms. Knowledge Improvement: At least an 80% average improvement in policy-related knowledge among participants, as measured by pre and post-workshop assessments. This will involve administering brief surveys before and after each session to quantitatively evaluate the increase in understanding of institutional policies. Application of Knowledge: Within six months post-workshop, at least 60% of respondents report successfully applying workshop insights to their work practices, as measured through follow-up surveys or interviews. This will assess the long-term retention and application of the policies covered in the sessions.
|  |  | Policy Feedback Mechanism: Establish a clear and accessible feedback mechanism where researchers and managers can provide input on existing policies and practices. This could be through focus groups, update forums, an online suggestion box or attendance at relevant away days/school based meetings. This feedback will inform policy reviews and updates, ensuring that policies remain relevant and responsive to the needs of researchers. | Yes (ECI2) | 2025-07-01 | RIG | A notable increase in constructive feedback received through the policy feedback mechanism, indicating active engagement and investment by researchers and managers in policy development and implementation. 45% of all respondents to CEDARS will agree that the institution values their contribution to institutional policy & decision making (31% of all respondents agreed in 2023 survey).
|  |  | Each area to have its own specific EDI Action Plan, including race equality objectives (in conjunction with the Inclusive Self Assessment Tool). Plans should readdress disparity across protected characteristics at a School/Service level. | yes (ECI2) | Start in Jan 2024 and coincide with annual business planning 2024 – 2027. | Associate Director - Equality, Diversity and Inclusion | All Schools/Services will have a specific EDI Plan with KPIs informed by data, scrutinised by the University Executive Team and in aggregate by the Board of Governors. | (Race Equality Charter Action Plan 2.2, 7.4, Athena SWAN Action Plan AP2)
| ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Conduct a Research Environment and Culture Audit: Conduct a comprehensive audit to assess the current research culture at LBU. This may involve surveys and assessments covering various aspects of the research environment, including inclusivity, collaboration, resources, work-life balance, and support systems. Use a mixed-methods approach involving quantitative surveys and qualitative interviews or focus groups to gain a well-rounded understanding. | Yes (ECI6) | 2024-06-01 | PVC for R&I | Achieve a participation rate of at least 60% in the audit to ensure broad representation. Comprehensive analysis completed, with key strengths and improvement areas identified.
|  |  | Develop an Action Plan Aligned with CEDARS/HREiR action plan: Following the research environment audit, a detailed action plan will be developed that aligns with this action plan and the existing CEDARS action plan. This plan will identify and prioritise areas for improvement based on the audit findings. The action plan will include specific, measurable, achievable, relevant, and time-bound (SMART) measures and will be communicated clearly to all stakeholders. | Yes (ECI6) | 2024-03-21 | The Academy | Timely development and implementation of the action plan within six months post-audit. At least 30% of the planned actions initiated within the first year of implementation.
|  |  | Research Insights Roundtable: Set up 'Research Insights Roundtable' events led by senior management, designed as open forums for researchers to share insights and provide feedback on the research environment and culture. These sessions will be widely accessible and promoted to encourage broad participation. | Yes (ECI6) | 2025-05-01 | The Academy | Aim to schedule 'Research Insights Roundtable' events bi-annually targeting a minimum participation of 10% of research staff per event. Thoroughly document feedback from each session, clearly showing its influence on university decisions and actions. Prioritise making these events broadly accessible and actively promote them to encourage extensive participation from the research community.
| ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Explore Recognition of Contributions in Research Promotion: Discuss and explore the potential for including active contributions to the development of a diverse research community as a factor in the criteria for research route promotion. This will be aligned to the activity in EI1 in relation to research staff roles and structures. | No | 2027-02-01 | PVC for R&I | Document the outcomes of discussions and explorations, with a goal to present findings and recommendations to the relevant university committees or bodies within 18 months. Success will be measured by the establishment of a clear roadmap or set of recommendations on how contributions to research culture might be integrated into promotion criteria.
|  |  | Implement Narrative CV Approaches: Develop and pilot the use of narrative CV formats to highlight and value contributions to the development of others and the broader Research & Knowledge Exchange (R&KE) community. | No | Implementation by Sep-25 | The Academy | Achieve a 50% adoption rate of the narrative CV format among researchers within three years, with positive feedback on its effectiveness in showcasing diverse contributions.
|  |  | Expand Early Career Researcher (ECR) Engagement Networks: Develop and enhance a comprehensive network framework for Early Career Researchers (ECRs) at the university level, while also exploring involvement in regional and national networks. This initiative will focus on fostering collaboration, support, and professional development, and will assess the feasibility and benefits of engaging with established external networks where possible. | No | Implementation by Sep-25 | The Academy | Establishment and operationalisation of a cross-university ECR network, achieving active participation from at least 30% of ECRs in year 1 and a 20% increase in year 2. In parallel, engage in discussions with a minimum of two external networks, both regional and national, to explore collaborative opportunities. Create a strategic plan outlining potential partnerships and joint initiatives with these external networks, setting a clear direction for ECR engagement and development.
|  |  | Expand ECI6 'Research Insights Roundtables' through Cafés: Enhance the existing 'Research Insights Roundtable' action (ECI6) by integrating 'Research Café' sessions, specifically designed for Postgraduate Researchers (PGRs) and research staff. These cafés will complement the roundtable discussions, providing a more informal setting for knowledge exchange, community building, and peer-to-peer learning. | No | 2025-09-01 | The Academy/Graduate School | Conduct at least two research café sessions per year with an average attendance of 25% of the target audience in first year of implementation and 15% increase the following year. Ensure these sessions are effectively interwoven with the 'Research Insights Roundtable' events to offer a diverse range of engagement opportunities.
31:323:32 |  |  | Form an implementation and evaluation group post-audit: Following the research culture audit (ECI6), a group will be formed comprising of researchers from various career stages to evaluate the audit findings, and respond and implement necessary actions. | No | 2025-03-01 | The Academy | ECI6: Timely evaluation, development and implementation of the action plan within six months post-audit. At least 75% of the planned actions initiated within the first year of implementation.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers. LBU's commitment to strengthening wellbeing and mental health is a priority, and this commitment is reflected in the comprehensive rollout of Wellbeing Assessments and mental health training for all staff. These initiatives are underpinned by regular reviews and the identification of good practices, encouraging conversations about wellbeing to be integrated into daily university life.
| ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Complete the launch of Wellbeing Assessments across the whole University (including all Schools). At LBU, Schools and Services are accountable for making sure that conversations about wellbeing at work and work-related stress take place, and for developing appropriate actions in response. The Wellbeing Assessment provides a simple structure for these conversations and enables us to proactively monitor and manage wellbeing and risk at a School, Service, and organisational level. | No | 2024-08-01 | Deputy Director of Human Resources | All Schools and Services complete a Wellbeing Assessment every 6 months. Good practice and wellbeing risks are identified across the University – share examples of good practice. Risk themes to inform wellbeing priorities (and reported on University Risk Register). | One of the most positive responses to our 2022 Colleague Survey was that 81% of respondents agreed with the statement “I believe my manager cares about my wellbeing”.
|  |  | Linked to our University Mental Health Charter Award, we submit evidence of progress against our Improvement Plans to Student Minds on an annual basis. Actions to promote good mental health and wellbeing include: Design and launch an all colleague mental health online training course as a part of induction for all staff. The module will include mental health, self-care, and supporting others. We will assess and identify groups who require additional support, training, briefing or signposting – likely to include security staff, accommodation staff, Academic Advisers and researchers (it is recognised that researchers undertake a range of potential roles – as a student, staff member (may include teaching responsibilities/working with students), may be based in an external organisation linked to research). | No | Dec-25 Aug-26 | Deputy Director of Human Resources | % increase in knowledge and confidence about talking about mental health. These measures will be built into the training – pre training and post training. In addition, there is a planned 6 month follow up to ask again about knowledge and confidence, plus whether individuals have had a conversation about mental health following the training. Self assessment tool to be determined, to include pre and post training review (similar to measures for all colleague mental health online course).
| ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | See ECI3 above regarding our University Mental Health Charter award and related actions. | No | See ECI3 | Deputy Director of Human Resources. | see ECI3 action
| ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | no specific action being prioritised against this obligation for the period of this action plan | No | h/a | n/a | CEDARS Question: To what extent do you agree that your institution promotes the importance of good mental health and wellbeing of staff - baseline 2023 55% agree Your working environment supports your mental health and wellbeing - baseline 2023 46%
| ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | CEDARS Question : To what extent do you agree your institution treats you fairly in relation to: Requests for flexible working. Baseline 2023 73% Maternity, paternity, adoption and parental leave. Baseline 2023 39% (not applicable to 57%) CEDARS Q25: managers' confidence in their ability to manage requests for flexible working appropriately. Baseline 2023 86%
| ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | CEDARS Question: To what extent do you agree that you take positive action to maintain your mental health and wellbeing? Baseline 2023 56% of managers of researchers
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents. LBU is committed to creating and maintaining a safe, welcoming and inclusive community which nutures a culture of respect and consideration for all. The aim of this obligation is to provide a robust reporting tool and support to address incidents of discrimination, bullying and harassment.
| ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Continue to review and amend (as required) Support, Report and Respect tool institutionally and jointly with Student Services. Implement an ongoing communication and marketing plan to raise awareness of the reporting tool for colleagues and students. Alongside delivery of education and training sessions. | No | Quarterly review of data to inform annual EDI training plan. | Associate Director - Equality, Diversity and Inclusion | Quarterly report on the number of submissions to the Support, Report, Respect platform to EDI Committee and our Governors Finance, Staffing and Resources Committee. Further outcomes to be determined following diagnostic work.
| ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | CEDARS Question: I would feel comfortable reporting an incident of discrimination - Baseline 2023 66% I would feel comfortable reporting an incident of bullying or harassment - Baseline 2023 59%
| ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | CEDARS Questions: Baseline 2023: 65% of respondents are familiar with the process for reporting incidents of discrimination; 66% would feel comfortable reporting an incident. Q38 Baseline 2023: 63% of respondents are familiar with the mechanisms to report bullying or harassment; 59% would feel comfortable reporting an incident.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion. An important part of LBU's strategy is to be "An excellent, diverse, engaged community". Equality, diversity and inclusion are integral to our culture and at the core of how we work with all members of our community. Connected to our values we want everyone at LBU to feel a sense of belonging. The aim of this obligation is to support managers and researchers to be aware of and adopt practices to enhance equality, diversity and inclusion.
| ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | To provide a high-quality annual programme of EDI training to the university community. | No | January 2025 (annual activity thereafter) | Associate Director - Equality, Diversity and Inclusion | Launch of 10 new EDI courses for enrolment across the University, including neurodiversity, sexual misconduct, re:tention, religion & belief awareness sessions. Increased uptake of EDI training offer from across the institution (baseline, and increase, to be determined following launch of the new training programme). | (Race Equality Charter Action Plan 5.6, 6.5, Athena SWAN Action Plan AP9)
| ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | n/a
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in, aware of, and maintain high standards of research integrity, and are able to report infringements or misconduct. In response to CEDARS survey insights and feedback from the wider university, LBU is intensifying efforts to advance research integrity education, addressing both the 54% of CEDARS respondents unfamiliar with the Concordat to Support Research Integrity and the 36% seeking further training. Our strategy prioritises comprehensive training and clearer communication of initiatives to elevate research integrity, and through these actions, we aim to cultivate a well-informed community, committed to exemplary research conduct.
| ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | Finalise and Implement the Responsible Research Umbrella Statement: Complete the approval process for the Responsible Research (RR) Umbrella Statement and integrate it into the university’s research policies, forming a comprehensive framework linking all research integrity, governance and ethics policies. | Yes (ECM2) | Implementation Sept-24 | RIG | Implement the RR Statement within one year of approval. RR statement will be included in policy awareness and feedback obligations/success measures noted in ECI2. Include institutional question in CEDARS to assess awareness and understanding of the statement among researchers and managers, aiming for a benchmark of 50% awareness.
|  |  | Promote Research Integrity through Workshops and Forums: Organise regular forums and workshops that address research integrity, focusing on national and international trusted research agendas. These events will aim to enhance understanding and application of best practices in research integrity among research staff, fostering a culture of ethical and responsible research. | Yes (ECM2) | 2025-09-01 | The Academy | Workshop/forum feedback: Achieve 90% positive feedback in terms of clarity, relevance, and practical applicability of the content, based on standardised post-session evaluation forms. Knowledge Improvement: At least an 80% average improvement in related knowledge among participants, as measured by pre- and post-workshop assessments. This will involve administering brief surveys before and after each session to quantitatively evaluate the increase in understanding of institutional policies. Application of Knowledge: Within six months post-workshop, at least 60% of respondents report successfully applying workshop insights to their work practices, as measured through follow-up surveys or interviews.
|  |  | Periodically review University Research Misconduct Policy and align with Sector Standards: Ensure the University Research Misconduct Policy and procedures fully align with sector standards, utilising UKRIO guidelines and templates. | Yes (ECM2) | Ongoing | RIG | Achieve full compliance with sector standards within one year. Monitor the policy’s effectiveness through annual review, focusing on case resolutions and adherence to guidelines.
|  |  | Implement Lessons Learned Reporting: Regularly report on and implement lessons learned from significant policy and procedure outcomes to continually improve research practices. | Yes (ECM2) | Ongoing | RIG | Document and disseminate an annual lessons learned as part of the R&KE annual report.
|  |  | Adopt the UKRIO RI Template: Implement the UKRIO Research Integrity template in full, following its successful pilot and sector-wide acceptance. | Yes (ECM2) | 2025-09-01 | RIG | Complete adoption within one year and conduct an annual review to assess its alignment and effectiveness with university research practices.
| ECM3 | Ensure managers report and address incidents of poor research integrity. | Enhance Managerial Training on Research Integrity: Expand the training for managers to include not only the identification and reporting of incidents of poor research integrity, but also to recognise and address questionable research practices early. Align this enhanced training with the UKRIO RI template and the University Research Misconduct Policy, focusing on preventative measures as well as responsive actions. | Yes (ECM2) | 2025-09-01 | RIG | Workshop/forum feedback: Achieve 90% positive feedback in terms of clarity, relevance, and practical applicability of the content, based on standardised post-session evaluation forms. Knowledge Improvement: At least an 80% average improvement in related knowledge among participants, as measured by pre- and post-workshop assessments. This will involve administering brief surveys before and after each session to quantitatively evaluate the increase in understanding of institutional policies. Application of Knowledge: Within six months post-workshop, at least 60% of respondents report successfully applying workshop insights to their work practices, as measured through follow-up surveys or interviews.
| ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | Expansion of the Actions in ECI2: Comprehensive Communication Strategy: Incorporate a segment specifically on research integrity and professional conduct within the broader communication strategy. Leverage the established channels noted in ECI2 to provide regular updates and insights into research integrity policies, promoting awareness and understanding among researchers and their managers. Integrate into Policy Awareness Workshops and Training Sessions: Include sessions on research integrity and professional conduct in the policy workshops noted in ECI2. Ensure that these sessions specifically address the responsibilities of researchers and their managers regarding integrity and professional conduct. Utilise Policy Feedback Mechanism for Targeted Feedback: Use the established feedback mechanisms to gather specific feedback on research integrity policies and their implementation. | No | See ECI2 | RIG | See ECI2
| ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | no specific action being prioritised against this obligation for the period of this action plan | no | n/a | n/a | CEDARS Question Baseline 2023: 58% indictated they are aware of mechanisms to report research misconduct (30% disagree), 61% indicated they trust LBU to investigate reported incidents (21% disagree), 66% would feel comfortable reporting an incident (21% disagree)
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution. Drawing on feedback from the wider university and CEDARS survey, which indicated a strong desire from 58% of all respondents, including early and mid-career researchers, to participate in policy and decision-making, LBU is committed to fostering an inclusive policy development process. With 45% of managers feeling valued for their policy contributions, yet a notable portion seeking greater involvement, our policy development efforts aim to expand formal engagement opportunities. By integrating researchers into decision-making bodies and establishing focused working groups, LBU strives to enhance the research environment, ensuring that a diverse range of voices is not only heard but also instrumental in driving institutional change.
| EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | Establish Consultation Mechanisms with the Professoriate Group: The role of the newly developed Professoriate as a consultative body on research and strategy will continue to be developed and promoted where necessary and appropriate. | No | 2025-04-01 | PVC for R&I | Conduct at least one consultation session per year with the Professoriate group, with documented feedback influencing decision-making processes and policy development.
|  |  | Broaden Researcher Involvement in School Committees: Increase researcher involvement in school committees, aiming to widen representation and the scope for researchers to contribute to decision-making. | No | 2025-04-01 | DoRs | Within three years, have researchers representing at least 40% of the membership on relevant school committees, and demonstrate their impact on policy through case studies or policy change records.
|  |  | Expand ECI6 'Research Insights Roundtables' Engagement: Extend the scope of Research Insights Roundtables to include discussions on organisational policy and decision-making, inviting researchers from various career stages. | No | 2026-05-01 | The Academy | See success measure in ECI6 Aim to increase the diversity of participation, targeting researchers from a variety of career stages, including early-career & fixed-term researchers, to ensure a comprehensive range of perspectives.
|  |  | Engage LBU researchers and managers in OR4 activities. Encourage participation in OR4 as a community of practice, and feedback mechanisms to shape LBU policies where appropriate in line with OR4 objectives. | No | 2025-01-01 | The Academy | Implement a feedback system to evaluate the engagement of LBU researchers and managers in OR4 activities, focusing on the depth of their contributions and the perceived impact on policy development. Aim to cultivate a rich narrative of positive changes and improvements in organisational policies, as informed by the OR4 community's insights and recommendations.
| ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Establish Policy Development Working Groups: Create short-life working groups within the Research and Enterprise Committee (REC), the University Research Ethics and Standards Committee (URESC), and Directors of Research (DoRs), to provide a formal structure for managers to contribute to policy development. | No | 2025-07-01 | RIG | Convene working groups on an as-needed basis for policy development, ensuring each group includes representation from at least 30% of research managers. Document the progress, and outcomes of these groups to capture their impact on policy development effectively.
|  |  | Leverage Existing Networks for Policy Discussion: Utilise the Heads of Subject network and other existing forums to facilitate discussions on policy development, ensuring that the voices of managers are heard and considered in policy formulation. | No | 2025-07-01 | RIG | Hold annual policy discussion sessions within existing networks and achieve at least a 40% participation rate from managers of researchers. Document the outcomes of these discussions to capture their impact on policy development effectively.
| EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | n/a
| ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Researchers will be encouraged to engage in the actions of ECI2 through the actions of ECR1 (ECR networks, Research Café's etc) | Ongoing | See ECI2/ECR1 | The Academy | See ECI2/ECR1 success measures.
| ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | no specific action being prioritised against this obligation for the period of this action plan | No | N/A | N/A | CEDARS Question Baseline 2023: 31% of respondents feel valued for contributions made to instiutional policy and decision making.
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation. CEDARS survey feedback indicates the majority perceive the recruitment process as fair, inclusive, merit-based, and transparent. The survey also revealed that over half of the respondents found local induction processes beneficial, prompting the development of research mentoring to enhance these inductions. This strategic initiative aims to integrate researchers seamlessly into our academic community, fostering their growth through a culture of collaborative learning and feedback.
| EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Review and take a stocktake of research staff roles and structures. Develop a profile to meet workforce strategy/strategic priorities. This action will be aligned to the activity in ECR1 related to research promotion. | yes (EI1) | 2026-07-01 | PVC for R&I with support from DoRs/HR/Academy | Complete a review and stocktake of research staff roles and structures by the end of the second year and make recommendations based on findings and as appropriate.
|  |  | Our Athena SWAN Action Plan includes an objective “Ensure that women (and men) of colour" are not disadvantaged through our recruitment processes and hiring culture” and related actions. | yes (EI1) | Dec-26 | Deputy Director of Human Resources | Improve interview to appointment rates for women of colour academics by 5% by 2026 (Current rates are 41% applications, 25% short-listed and 11% for BAME women academics) (Athena SWAN Action Plan.) | (Athena SWAN Action Plan AP10)
|  |  | Declaration of Commitment and Best Practice Guidance: Officially release a declaration of the university's adherence to the DORA and/or CoARA principles and furnish senior staff with detailed guidance on exemplary practices in evaluating researchers during recruitment, promotions, and award processes. This will incorporate the CREDiT taxonomy and the Résumé for Researchers toolkit as developed by the Royal Society. | yes (EI1) | 2024-12-01 | PVC for R&I | Issue the commitment declaration and circulate the guidance, aiming for a minimum of 60% awareness amongst senior staff by the end of year 2, as gauged by a institutional question in CEDARS.
|  |  | Implement, Evaluate, and Integrate OR4 and/or DORA/CoARA Principles: Joint R&I and HR review to recommend updates to the university's recruitment, promotion, and evaluation policies to ensure they align with the DORA/CoARA and OR4 principles (of which LBU is a institution of practice). This action will focus on embedding a more holistic and equitable approach to recognising a wide spectrum of academic contributions, including responsible research assessment and Open Research practices. | yes (EI1) | 2026-07-01 | RIG | Provide a comprehensive list of recommendations for policy updates by the end of Year 2.
|  |  | Join the UK Reproducibility Network (UKRN) and Promote Reproducibility Practices We will join the UK Reproducibility Network (UKRN) to demonstrate our commitment to robust and transparent research practices. | yes (EI1) | 2024-12-01 | The Academy | By the end of the first year, establish a formal partnership with UKRN, with documented integration of reproducibility criteria in recruitment guidelines.
| EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Central Research Mentoring Programme: Launch a centralised research mentoring programme, incorporating reverse mentoring, tailored to new research staff. This programme will complement existing school-based schemes, pairing new researchers with experienced mentors and vice versa to facilitate mutual learning and integration into the university's research community and policies. | No | 2025-07-01 | The Academy | Achieve a 100% pairing rate of new research staff with mentors, including reverse mentoring pairings, within one month of receiving a mentoring request. Aim for annual satisfaction feedback from mentees and mentors, including participants in reverse mentoring, with a target of at least an 85% positive response rate regarding the programme's value and support.
|  |  | Mentorship Resource Development: Create and disseminate a comprehensive resource pack for mentors, including key university policies, effective mentoring practices, and pathways to research development opportunities. This will support mentors in providing consistent and informed guidance. Specific resources will be provided to support those on fixed-term contracts. | No | 2025-07-01 | The Academy | Ensure that all mentors have accessed and engaged with the mentorship resources within the first three months of the programme launch, with a follow-up survey indicating that 90% find the materials beneficial for their mentoring role.
|  |  | Enhancement and Integration of Research Induction Programmes: Further develop the existing central research induction programme to ensure comprehensive coverage of university policies, research practices, and community integration, while also ensuring alignment with and enhancement of school-specific inductions. | No | 2026-07-01 | The Academy | Evaluate the effectiveness of the research induction program by achieving at least 90% satisfaction in feedback from new research staff, gauging the program's comprehensiveness and relevance. Utilise surveys, focus groups, and Research Network forums to gather detailed feedback from new starters, with the goal of continuously refining the program to ensure it effectively integrates staff into the university's research community. CEDARS Survey Question: Include a targeted question in the next CEDARS survey to assess the impact of the research induction on new staff, aiming to have the majority report that the program significantly contributed to their successful integration into the research environment.
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression. Equitable and merit-based advancement is essential for the professional development of researchers. We will evaluate and improve our promotion policies to increase the diversity and range of candidates across all advancement pathways.
| EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | The Strategic workforce plan includes defining the LBU Academic and creating a framework of typical responsibilities. | yes (EI3) | 2024-09-01 | Deputy Director of Human Resources | Framework of typical activities/responsibilities published and ready for 2024 academic year.
|  |  | Continue to assess and monitor the Academic Promotion Policy and make improvements to widen the diversity and range of applicants through all pathways. | yes (EI3) | 2024-09-01 | Deputy Director of Human Resources | Completion of Equality Impact Assessment of Academic Promotion process. Further outcomes to be determined following diagnostic work.
|  |  | Explore Integration of OR4 and Narrative CV Insights into Recognition Working with HR, explore how insights from the OR4 project and the practices of narrative CVs could potentially inform and enhance the university's recognition processes. | yes (EI3) | 2027-07-01 | The Academy | By the end of year 3 discussions will be documented included future actions as appropriate.
| EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | see above | n/a | N/A | N/A | n/a
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
| EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | no specific action being prioritised against this obligation for the period of this action plan | n/a | n/a | n/a | CEDARS Q25. Managers' confidence in relation to: Giving guidance to researchers on redeployment processes. Baseline 2023= 32% confident/fully confident.
| ER1 | Researchers ensure that they work in accordance with institutional policies, procedures and employment legislation, as well as the requirements of their funder. | no specific action being prioritised against this obligation for the period of this action plan | n/a | n/a | n/a | n/a
| ER2 | Researchers understand their reporting obligations and responsibilities. | no specific action being prioritised against this obligation for the period of this action plan | n/a | n/a | n/a | n/a
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews. We are enhancing the support for research managers with targeted leadership and project management training, responding to the CEDARS survey where over half expressed a desire for such development. We're focused on equipping our managers with the skills necessary to effectively lead and innovate, thus reinforcing our dedication to research excellence.
| EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | Enhancing Research Leadership and Project Management Training Implement a comprehensive Research Leadership and Management training pathway for all potential and newly appointed research managers, including project management, financial oversight, and effective mentorship. | yes (EI4) | 2024-12-01 | The Academy | Leadership Pathway Completion: Achieve a 60% completion rate for the Research Leadership and Management Training Pathway among eligible staff within the first 18 months of its launch.
|  |  | Enhancement of Project Management Training Develop and implement a dedicated Project Management Training Programme specifically designed for researchers and research managers, focusing on effective research project execution, financial management, and strategic alignment with the university's research goals. | yes (EI4) | 2025-12-31 | PAT | Workshop/forum feedback: Achieve 90% positive feedback in terms of clarity, relevance, and practical applicability of the content, based on standardised post-session evaluation forms. Knowledge Improvement: At least an 80% average improvement in related knowledge among participants, as measured by pre- and post-workshop assessments. This will involve administering brief surveys before and after each session to quantitatively evaluate the increase in understanding of institutional policies. Application of Knowledge: Within six months post-workshop, at least 60% of respondents report successfully applying workshop insights to their work practices, as measured through follow-up surveys or interviews.
| EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | See EI3 and PCDI3 for related actions | No | See EI3/PCDI3 | Deputy Director of Human Resources | See EI3 and PCDI3 for related success measures
| EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS Q25. Managers' confidence in relation to: Manage appraisal/review processes effectively. Baseline 2023 = 100% CEDARS Q26: Percentage of managers who report having undertaken training and other CPD in: Conducting appraisals. Baseline 2023 = 74% Leading a research group. Baseline 2023 = 42% Managing staff performance. Baseline 2023 = 58% Supervising doctoral researchers. Baseline 2023 = 82% Leadership. Baseline 2023 = 78%
| EM4 | Managers actively engage in regular constructive performance management with their researchers. | Look at PDR process/principles to enable excellent PDR conversations, to include how often, who and development for reviewers. | No | Sep-24 | Deputy Director of Human Resources | Principles embedded in essential PDR resources for all colleagues. Better understanding of our data in connection with PDR conversations.
| ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS: Percentage of respondents who report having received an appraisal. Baseline 2023: 89.4%
Job security
The aim of this obligation is to improve the job security of researchers. Through the integration of job security strategies into our mentoring programmes, we aim to provide comprehensive support to our research staff, assisting them in understanding the intricacies of employment transitions within academia and maximising their career development opportunities.
| EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | expanding EI2 Research Mentoring action Incorporate Job Security into Mentorship Programme Resources (EI2) Develop mentorship programme resources to include enhacement of job security for researchers. The tailored resources will aim to support new and existing research staff and those on fixed term contracts in understanding redeployment processes (as appropriate), exploring open-ended contract opportunities, and navigating career development paths within the university. | No | 2025-12-31 | The Academy | Develop with programme and resources noted in EI2 along with associated success measures.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it. We recognise the crucial role that professional development plays in advancing the careers of our researchers. The Academy for Research & Knowledge Exchange is central to this vision, providing structured and personalised pathways integral to our strategy for fostering research excellence. We are committed to ensuring that researchers have the necessary time and resources to embrace these opportunities, which are essential for their development across various employment sectors. With the key priorities of this section being focused on delivering an enhanced and tailored development programme, as well as mentoring and career development support for our researchers, we are dedicated to the ongoing advancement of our research staff, ensuring alignment with the dynamic nature of their professional journeys.
| PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Establish and Develop The Academy for Research & Knowledge Exchange We will establish the structural foundation for The Academy, securing academic input and resource planning. Following this, we will craft a 3 - 5 year strategic delivery plan that outlines the trajectory for The Academy’s development and engagement with the university's research and teaching staff. | yes (PCDI1) | 2024-12-01 | Director of R&KE | By the end of Year 1, have The Academy’s strategy and three year work plan approved and in place.
|  |  | Create a Co-ordinated Researcher Development Programme Develop a Researcher and Knowledge Exchange Development Programme, co-created with input from academic staff and aligned with existing school-based offers, to support staff in achieving their full potential in research, innovation, and collaboration. | yes (PCDI1) | 2024-12-01 | Director of R&KE | Launch the initial phase of the programme by Year 2, with at least 50% of research staff engaged in the new development activities. By Year 3, achieve a satisfaction rate of 90% among participating staff, with evidence of professional development impact collected through feedback and progress tracking.
|  |  | Tailored Development Pathways Design and implement personalised development pathways by career stage that address the unique career goals of researchers, offering a blend of online and in-person workshops, seminars, and mentorship opportunities. | yes (PCDI1) | 2026-07-01 | The Academy | By the end of year 2, establish tailored development pathways for each career stage, incorporating feedback from our target audience via focus groups and other engagement mechanisms. We will introduce an annual review process, combining qualitative insights and quantitative data, to assess the effectiveness of these pathways and make necessary adjustments. By year 3, we aim for at least 80% of researchers who engaged to positively report that the development opportunities have tangibly supported their career progression.
|  |  | Enhance Career Development Integration in PDRs Explore the incorporation of career development discussions into a refresh/review of Academic staff PDR resources for 2025 PDR cycle, particularly for research colleagues as noted in ECI1 | yes (PCDI1) | 2025-12-31 | DoRs | Conduct an evaluation of the current PDR resources with respect to career development in the second year, leading to recommendations on potential enhancements.
| PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | Integration of Professional Development Recording in Symplectic Elements Explore the potential for Symplectic Elements to record and track researchers’ professional & career development activities, offering a structured and transparent system for documenting career progression. | No | Ongoing | LSS | Conduct a feasibility study by the end of Year 1 and, if viable, present a proposal to REC. Following approval, aim to implement the recording feature by the end of Year 2 and achieve 50% researcher engagement with the system by Year 3.
| PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS: the extent to which researchers agree that: Your manager/supervisor encourages you to engage in personal and career development activities. Baseline 2023 = 63%
| PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | No specific action has been prioritised against this obligation for the period of this action plan. | N/A | N/A | N/A | CEDARS: The extent to which researchers agree that their immediate line manager: supports me in my broader career aspirations. Baseline 2023 = 49%
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews. We recognise the necessity for more structured career development conversations, as evidenced by a significant proportion of respondents in the CEDARS survey highlighting the lack of regular formal career development reviews and expressing a need for wider career guidance. Accordingly, we are enhancing our training and support systems to enable managers to conduct meaningful career development reviews, with particular emphasis on supporting researchers on fixed-term contracts who may require additional assistance in charting their career paths within and beyond academia. This initiative aligns with our commitment to ensure that all researchers, with the support of their managers, have clear and actionable career development plans.
| PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | Enhance Managerial Capacity for Career Development Reviews Develop a comprehensive training programme for managers of researchers, with a focus on conducting effective peformance and career development reviews. This programme will include best practices for supporting researchers, particularly those on fixed-term contracts, and strategies for balancing managerial duties with research responsibilities. | No | Implementation by Sep-25 | The Academy | Workshop engagement and feedback: By Year 2 post-implementation, ensure 60% of managers have accessed training resources in effective career development review techniques. Achieve 90% positive feedback in terms of clarity, relevance, and practical applicability of the content, based on standardised post-session evaluation forms. Knowledge Improvement: At least an 80% average improvement in related knowledge among participants, as measured by pre- and post-workshop assessments. This will involve administering brief surveys before and after each session to quantitatively evaluate the increase in understanding of institutional policies. Application of Knowledge: Within six months post-workshop, at least 60% of respondents report successfully applying workshop insights to their work practices, as measured through follow-up surveys or interviews.
|  |  | Expanding on EI2 related action: Promote Interdisciplinary Research Mentoring Integrate a research mentoring scheme that spans across disciplines, offering training and support to both mentors and mentees. This will facilitate a broader understanding of research impacts across different fields, particularly in curriculum development. | No | 2025-07-01 | DoRs | EI2 Success Measure: Ensure that all mentors have accessed and engaged with the mentorship resources within the first three months of the programme launch, with a follow-up survey indicating that 90% find the materials beneficial for their mentoring role.
|  |  | Leverage and Publicise External Career Development Opportunities Create a central repository of external career development events and initiatives, promoting them within the university to enhance researchers' and managers' awareness of external growth opportunities. | No | 2025-07-01 | The Academy | CEDARS: 80% of respondents will indicate they agree/strongly agree to Q: You are aware of the support your institution provides for your career and professional development (CEDARS 2023 baseline = 49%)
| PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | See action in PCDI6 (professional development) | No | Ongoing | The Academy | See PCDI6 (professional development) success measure CEDARS: 50% of respondents to indicate they have had a formal career development review (CEDARS 2023 baseline 33.8%)
| PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | See PCDI1 "Enhance Career Development Integration in PDRs" | yes (PCDI1) | 2025-09-01 | The Academy | PCDI1 success measure "Conduct an evaluation of the current PDR resources with respect to career development in the second year, leading to recommendations on potential enhancements" CEDARS: 50% of respondents to indicate they have had a formal career development review (CEDARS 2023 baseline 33.8%)
|  |  | Leverage OR4 insights to inform career development discussions. Managers at LBU will be equipped with OR4 resources to guide meaningful career development conversations, focusing on responsible research practices. |  | 2026-09-01 | The Academy | By the end of Year 2, gather qualitative feedback to assess the reception and perceived impact of integrating OR4 principles into career development conversations. The feedback will inform further refinements.
| PCDR4 | Researchers positively engage in career development reviews with their managers. | no specific action being prioritised against this obligation for the period of this action plan | N/A | N/A | N/A | CEDARS Q30: the extent to which researchers agree that: You have a clear career development plan. Baseline 2023 = 40%
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience. Comprehensive career development support is integral to the professional growth of our researchers. The gap highlighted by CEDARS, where a noticeable number of researchers have not had career conversations with specialists and remain unaware of the support mechanisms in place, underscores the need for enhanced guidance and resources. We are committed to enhancing career development planning and aim to enrich the environment for professional advancement, ensuring that every LBU researcher is equipped with the knowledge and tools to create a robust and dynamic career pathway, reflective of the diverse opportunities within the academic landscape and beyond.
| PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Expansion of ECR1 Implementation of Narrative CVs for Career Development Initiate the use of narrative CVs to provide researchers with a format to comprehensively document their skills, achievements, and contributions, supporting recognition of diverse research activities. | yes (PCDI3) | Implementation by Sep-25 | DoRs | Within the first year following implementation, develop guidelines and training on creating narrative CVs. By Year 2, achieve at least 40% of researchers trained in developing narrative CVs. Impact for ECR1: Achieve a 50% adoption rate of the narrative CV format among researchers within three years, with positive feedback on its effectiveness in showcasing diverse contributions.
|  |  | Career Development Workshops and Seminars Organise regular workshops and seminars focused on career management, skills transferability, and career progression within and beyond academia, particularly addressing the unique needs of those on fixed-term contracts. | yes (PCDI3) | Implement by Sept 2025 | The Academy | Workshop engagement and feedback year 1 post implementation, ensure 40% of researchers, including a significant proportion from fixed-term contracts, have attended training. Achieve 90% positive feedback in terms of clarity, relevance, and practical applicability of the content, based on standardised post-session evaluation forms. Knowledge Improvement: At least an 80% average improvement in related knowledge among participants,, with focused analysis on the responses from fixed-term contract staff, as measured by pre- and post-workshop assessments. This will involve administering brief surveys before and after each session to quantitatively evaluate the increase in understanding of institutional policies. Application of Knowledge: Within six months post-workshop, at least 60% of respondents report successfully applying workshop insights, as measured through follow-up surveys or interviews.
| PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | See ECR1/PCDI2 actions related to Narrative CVs | No | See ECR1/PCDI2 | The Academy | See impact in ECR1/PCDI2
|  |  | See action PCDI6 related to Integration of Professional Development Recording in Symplectic Elements | No | Ongoing | The Academy | See action PCDI6
|  |  | Integration of Narrative CV Guidance into Existing Panel Member Training: Incorporate information and examples of narrative CVs into the existing training materials for panel members, ensuring they are equipped to recognise and evaluate the broad range of contributions detailed in such CVs. | No | 2027-07-01 | The Academy | Narrative CV content will be embedded into all relevant panel member training materials by the end of Year 3. Success will be gauged through qualitative feedback from panel members on the utility of the narrative CV information in enhancing their evaluation process, with the aim of establishing a more holistic understanding of candidates’ capabilities and achievements.
Research identity and leadership
The aims of these obligations are to provide researchers with the opportunity to progress in their careers by developing their research identity and leadership capabilities. Feedback from the CEDARS survey has shown that a significant portion of respondents feel they lack the time and support necessary to develop their research identity. In response, we are ensuring that the specialised modules within the Academy’s programs, as well as the expansion of narrative CV workshops, are tailored to empower researchers to refine their unique identities and leadership skills
| PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | Integrate Research Identity Development in the Academy Programmes Expand the Academy for Research & Knowledge Exchange's programmes (PCDI1) to include specific modules aimed at developing researchers' unique identities and leadership skills within the academic and broader research community. Utilise OR4 project findings to develop training and development programs that align with Open Research practices and responsible research assessment. | No | Dec-25 Dec-26 | The Academy | CEDARS: 60% of respondents will indicate thay have time to develop their research identity (2023 baseline = 35% Launch of at least one new training program or workshop series by Year 2, based on OR4 project findings, with a participation rate of 40% among LBU researchers.
|  |  | Broaden the Scope of Narrative CV Workshops Leverage the existing narrative CV framework (ECR1/PCDI3/PCDR3) to encompass broader aspects of research identity and leadership, providing a more comprehensive tool for researchers to articulate their career trajectory and impact. | No | Implementation by Sep-25 | The Academy | See impact in PCDI3
|  |  | To promote and maintain a vibrant research community of BAME academics at all stages of their career with LBU. | No | Start Sept 2023. End Sept. 2027. | Associate Director - Equality, Diversity and Inclusion | Minimum of 1 event annually. Minimum of biannual networking and peer support activity. Published communications of outcome from members. | (Race Equality Charter Action Plan 5.12)
| PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | CEDARS Q30: the extent to which researchers agree that: You have time to develop your leadership skills. Baseline 2023 = 30% You have time to develop your research identity. Baseline 2023 = 35%
| PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | Research Leadership Management Training Broaden the scope of the Research Leadership and Management Training (EI4) to include advanced modules for established managers, focusing on strategic leadership, change management, and fostering a positive research culture. | No | 2024-12-01 | The Academy | See EI4 impact
| PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | no specific action being prioritised against this obligation for the period of this action plan | No | n/a | n/a | n/a
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research. LBU acknowledges the aspirations of our research community to engage more deeply with external sectors and translate their work into societal impact, as reflected in the CEDARS survey where a majority expressed an interest in training for public engagement, knowledge exchange, and policy development. Responding to this, we will enhance the Festival of Research & Knowledge Exchange, which serves as a platform for researchers to cultivate skills in these key areas. This initiative, alongside exploring research mobility and secondment opportunities, underlines our commitment to fostering a dynamic, interdisciplinary environment where researchers are empowered to extend their influence beyond academia.
| PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | Facilitate Research Mobility and Secondment Opportunities In collaboration with HR, conduct an exploratory review to assess the current state of mobility and secondment opportunities within and outside the university. Develop a brief that outlines potential strategies to support and enhance these opportunities for researchers. | No | 2027-07-01 | DoRs | Successfully complete the exploratory review on research mobility and secondment opportunities, and present the findings, along with associated next steps, to the Research and Enterprise Committee (REC) by the end of year 3.
| PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | See actions in EI2/PCDI2 (mentorship) and PCDI3 (Career Development) | Yes (PCDM2) | EI2/PCDI2 | The Academy | See impact in EI2/PCDI2 (mentorship) and PCDI3 (Career Development)
| PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | no specific action being prioritised against this obligation for the period of this action plan | n/a | n/a | n/a | n/a
| PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | Annual Festival of Research & Knowledge Exchange Via the annual Festival of Research & Knowledge Exchange, we will enhance researchers' awareness and experience of the wider research system, including knowledge exchange, policy development, public engagement, and commercialisation. This may involve curated workshops, collaborative projects with industry, and opportunities for public outreach. | No | Ongoing | The Academy | Engagement: Enhance data management concerning engagement from target beneficiaries, with the objective of achieving a 20% year-on-year increase in participation rates. Case Study Development: Develop comprehensive case studies that showcase the application and benefits of knowledge exchange activities. These should include quantifiable outcomes where feasible, along with testimonials from researchers that highlight the value derived from the festival.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
| Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
| 1 | OR4 Project |  |  |  | PVC for R&I | Pro Vice Chancellor for Research & Innovation (Prof Silke Machold)
| 2 |  |  |  |  | Director for R&KE | Director of Research & Knowledge Exchange (Dr Camelia Dijkstra)
| 3 |  |  |  |  | The Academy | The Academy for Research & Knowledge Exchange
| 4 |  |  |  |  | DoRs | Directors of Research
| 5 |  |  |  |  | REC | Research and Enterprise Committee
| 6 |  |  |  |  | OR4 | Open and Responsible Researcher Reward and Recognition Project
| 7 |  |  |  |  | PAT | Post Awards Team
| 8 |  |  |  |  | LSS | Library & Student Services
9
10
11
12
13
14
15
16
17
18
19
20