## Actions for 2017-2019
| HR Excellence In Research Action Plan | [5 empty] | COMPLETE
Link to Principles and previous HR Excellence in Research submission: http://www.leedsbeckett.ac.uk/research/hr-excellence-in-research-award-for-leeds-beckett/ | [6 empty] | Live - On Schedule
Planned - not started/not due
ACTIONS FOR 2017-2019 | [6 empty] | Behind Schedule - low priority
Behind Schedule - high priority
Principle / Section | Action | Link to other principles /sections of the Gap Analysis | Responsibility | Deadline | Success Criteria/Outcome Measures | Link to Athena SWAN/ People Strategy / Concordat Principle | Status | Comments
Principle 1: Recognition of the importance of recruiting, selecting and retaining researchers with the highest potential to achieve excellence in research.
1.2 | The People Strategy 2016-2021 includes a number of KPIs around the attraction of great people, including “monitoring of retention rates in first year of employment”. These KPIs will be regularly monitored. | 1.3, 1.4, 2.6, 6.3 | Human Resources | August 2021 | 30% of new staff attracted by the University’s reputation. The percentage of staff recruited within the last 12 months who have left the University voluntarily to be below 9.3% (DLA Piper HE Benchmark). | Concordat Reference A2 | COMPLETE | The HR New Starters survey was sent during March 2018 to all New Starters (staff) at Leeds Beckett University who took up their posts in the previous nine months. 31% indicated that reputation was one of the factors which attracted them to work at Leeds Beckett University. The DLA Piper Scorecard provides the percentage of staff recruited within the last 12 months who have left the Leeds Beckett voluntarily compared with the HE sector. On the 2018 Scorecard these percentages were 2.6% for Leeds Beckett, compared with 9.7% for the sector. Supported by an external consultant, we have commenced research to develop and understand our employer value proposition. The development of a distinctive, compelling employer brand that is attractive and authentic forms part of our recently refreshed People Strategy.
1.2 | Actions to increase the number of female applicants applying for academic positions, including a review of our job descriptions and shortlist criteria for terminology or phrasing which may be a barrier. | 2.6, 6.2, 6.3, 6.5 | Human Resources | December 2019 | Increase in the number of female applicants applying for academic positions by 30% by 2020. | Athena SWAN 2.2g | ONGOING | In early 2019, summary data was provided by School/Service as a first indication of when (and when not) to use positive action statements in adverts for different roles and grades to support and extend the appropriate use of positive action statements. HR have explored the use of the Total jobs gender calculator to review our recruitment documentation. This information will be shared with HR Business Partners for dissemination to Schools and Services. All external colleague recruitment adverts are placed on www.vercida.com/uk (a diversity and inclusion website), where there is also an organisation profile for Leeds Beckett. Our University news webpages include a "Research" news section https://www.leedsbeckett.ac.uk/news/?category=research to increase visibility of the University’s research outputs and interests as part of a concerted effort to feature male and female academic colleagues. For example, Professor of History at Leeds Beckett Heather Shore was featured in September 2018 to publicise her involvement in a new research collaboration to explore the history of victims' access to justice in England over the course of three centuries.
1.2 | Establish clearly at the outset of recruitment processes whether a role can be undertaken on a job share basis and communicate this through advertisements. | 2.6, 6.3, 6.5 | Human Resources | January 2018 | Jobs website and recruitment materials amended. | Athena SWAN 5.4a, 5.4b | COMPLETE | The Vacancy Review form (completed by managers at the outset of a recruitment process) has been revised to include the following question "Has consideration been given to advertising this post on a part-time, flexible working or job share basis?" Adverts refer to the wide range of benefits which can be accessed when working at Leeds Beckett, including flexible working.
1.3 | Report on the use of fixed term contracts for Research Assistants and Research Officers and review if action is required to reduce gender differences. | 1.2 | Human Resources | September 2018 | Ensure gender parity in relation to fixed term research contracts and continue to monitor the use of (and recruitment to) research fixed term contracts. | Concordat Reference A3 Athena SWAN 4.8a | COMPLETE | Analysis undertaken in 2019 - it was found that of the 21 researchers (Research Assistant/Research Officer/Research Fellow/Senior Research Fellow) on a fixed-term contract, 10 (48%) were female and 11 (52%) were male. A third of these fixed term researchers are within their first year of employment at Leeds Beckett.
1.4 | Monitor the diversity composition of recruitment panels and ensure that Chairs are drawing from the full pool of potential panel members rather than relying on the same few and that gender balance is provided from the core membership of the panel (not HR or external). |  | Human Resources | December 2019 | Monitoring of recruitment panel membership in place and analysis/report on a 6 monthly basis. | Athena SWAN 2.2d | ONGOING | Information on diverse panel composition is included in the revised guidance on panel composition (part of the Recruitment and Selection Policy and Procedure). The new recruitment online portal (launched March 2019) will better facilitate the monitoring of panel composition.
1.5 | Review our senior and professorial pay arrangements as part of the review of our approach to rewarding and recognising contribution and success | 2.5, 2.6 | Human Resources | December 2017 | Pay and grading review completed. | People Strategy (and Athena SWAN 2.4a) | COMPLETE | New arrangements were introduced in 2017 for an annual review of all senior and professorial pay. A Pay Review Panel meets to consider overall performance against strategic and personal objectives as well as other information such as relevant benchmark data, feedback and research grants/publications/supervision (as appropriate).
Principle 2: Researchers are recognised and valued by their employing organisation as an essential part of their organisation’s human resources and a key component of their overall strategy to develop and deliver world-class research.
2.1 | Our Equality Forums (Race, Gender, Disability, LGBT and Religion & Belief) will have a stronger presence and be more proactive in delivering events and activities. |  | Human Resources | December 2017 | Each forum supports national awareness days/months and hosts at least one event; Disability History Month, Annual Race Lecture, LGBT History Month, International Women’s Day, Interfaith Week. All events underpin delivery of the University’s Equality Objectives. |  | COMPLETE | Our equality forums are actively engaged in delivering events and activities. Annual Race Lecture took place on 18 October 2017 - "Sustaining Change in Workplace Race Equality: What Works and What Doesn’t" and on 17 October 2018 "Unearthing Submerged Narratives in Classical Music Histography and Education: Towards an Inclusive Art Form and its Teachings". The inaugural Gender Research Conference took place on 6 March 2018. This provided an opportunity for colleagues to share and celebrate the range of gender research being undertaken across the University, network with colleagues, and showcase Leeds Beckett’s gender research to external delegates. The University has taken part in the city's Leeds Pride parade and celebrations since 2014 as a visible statement of our commitment to LGBT+ equality. Over 100 colleagues, students and alumni took part in Yorkshire's biggest LGBTQ celebrations on Sunday 5 August 2018, with an estimated 40,000 people in Leeds city centre. Our equality forums and colleagues have led on several events in support of Disability History Month in December 2018, LGBT History Month in February 2019 and Women's History month in March 2019. These have incorporated research and practical applications and included - an exploration of how disability is portrayed in popular film, practical sessions on gender identity and trans awareness, an Aurora panel discussion with invited speakers and a week of events themed around women in research, history and sport.
2.3 | Academic staff will be actively encouraged by managers to take up promotion opportunities through the annual PDR process. | 3.2, 5.5 | Deans of School and Heads of Subject | December 2020 | Academic staff to have discussion of career development and promotion included in their PDRs. 40% of those women eligible to apply for a Reader or Professorship to attend a promotions workshop. | Athena SWAN 2.3d, 2.3f, 4.2b | ONGOING | Academic staff have been encouraged to attend sessions linked to their development. For example: All Directors of Research attended a group residential in April 2017 (and 90% attended a group away day in April 2018) and a development session 'Developing ourselves and others as Academic Change Leaders' took place in January 2018 for Directors of Research and Deans of School. Our refreshed People Strategy includes priorities to "modernise our approach to performance development so it enhances individual and team performance" and to "create career pathways that support our strategic priorities around learning and teaching, research and enterprise." It is anticipated that work to modernise our PDR process will commence during the 2019/20 academic year. Four open staff meetings were held in early January 2019 to provide guidance to those considering making an application under the University's annual academic promotions round, contributing to the continued investment in academic progression (see 2.6 below).
2.5 | A gender pay gap report (to include Equal Pay audit) will be undertaken in 2017 to analyse the percentage difference between the average pay of male employees and female employees for a given group. | 1.5 | Human Resources | December 2017 | Report produced and published on our webpages. |  | COMPLETE | The University’s 2017 and 2018 Gender Pay Gap reports have been published and action points developed https://www.leedsbeckett.ac.uk/public-information/equality-and-diversity/data/ We are pleased to report improvements in both the mean and median gender pay gap. Our University’s mean gender pay gap in 2018 was 9.5% which is a reduction from 2017 when it was 10.2%. The median pay gap was 7.7% and has also reduced from 8.4% in 2017. These figures represent positive progress and are significantly below the reported sector gender pay gap of 16.1%, as published by the Office for National Statistics (ONS). Nevertheless, we recognise that the gender pay gap continues to exist and we are committed to continuing to monitor and address this through the actions set out in this report.
2.6 | The promotions and regrading procedure will be reviewed as part of our review of our approach to rewarding and recognising contribution and success. | 3.2, 5.4 | Human Resources | December 2020 | Development of new options to reward and recognise contribution and success. | Concordat Reference B4.2 People Strategy | ONGOING | As part of the refreshed People Strategy, we are currently auditing our range of reward and recognition mechanisms, which will be informed by our organisational values and priorities alongside broader considerations including changes to the pension schemes and the outcomes of national pay negotiations. We are planning a longer term reward strategy for 2020 onwards.
2.6 | We will review our academic career pathways, including teaching, learning and research roles, and implement an annual academic promotion process. We will continue to enhance the use of developmental roles including the use of Graduate Teaching Assistants. | 1.2, 3.2, 3.4, 5.4 | Human Resources | December 2020 | Annual Academic Promotions process in place, supported by clear career pathways. Representation of women within the Professoriate to rise to 35% by 2020. | People Strategy (and Athena SWAN 2.3d) | ONGOING | A new annual process for promotion to Professor and Reader was launched by our Vice Chancellor in early May 2017, supported by a revised Academic Promotions Policy. In the 2017 round, 9 members of staff were promoted to Professor and 30 to Reader. In the 2018 round, 2 members of staff were promoted to Professor and 13 to Reader. In the 2019 round, 1 member of staff was promoted to Professor and 8 to Reader. In total, 19 females have been promoted to Reader and 6 females have been promoted to Professor through this process. Female representation within the professoriate is currently 30% (increased from 19.1% in 2014). There are currently 25 Graduate Teaching Assistants working at Leeds Beckett (this position offers aspiring academics the opportunity to study for a PhD, while lecturing in subjects broadly related to their area of research). The development of career pathways to support our strategic priorities around learning and teaching, research and enterprise remains a priority in our current People Strategy.
Principle 3: Researchers are equipped and supported to be adaptable and flexible in an increasingly diverse, mobile, global research environment.
3.1 | We aim to include sessions on ‘Research Impact’ and ‘Public Engagement’. | 3.9 | DVC (Research & Enterprise) | Summer 2018 | Staff Training schedule includes training on 'Research Impact' and 'Public Engagement' to include all levels of researchers from established to early for a maximum cohorts of 20 people. |  | ONGOING | The Research and Impact Agenda has become integral to our staff development programme and whilst the focus has been on the creation of Impact Case Studies for REF the learning will inform future workshops. The Graduate School works closely with the Impact Officers to create opportunities for research staff to learn about Impact and Public engagement. One such session was the 'Creating Research Impact in the Media' in collaboration with the Head of Communications. Our Impact Officers have continued to work closely with our DoRs to offer bespoke workshops, which have included an impact masterclass and impact writing bootcamps, where 30 research colleagues attended. Two external research impact consultants, Mark Reed, who delivered a one day masterclass and Saskia Walcott who delivered 2 x 2 day writing bootcamps, they offered our research staff impartial advice on their writing techniques and contents. They also offered 1:1 sessions to those who attended, in particular providing feedback and evaluation on their written works. This was very well received and has now propelled a number of internal bootcamps and 1:1s to take place by our Impact Officers. At School level there have also been workshops and development days on Impact and Engagement. The Carnegie School of Sport has ongoing links with Mark Reed’s nationally recognised Research Impact development days and has a ‘Carnegie Research with Impact’ unit that informs staff away days and staff research seminar series. The learning from these workshops will inform the Staff Development programme across the university moving forward. Our University wide Research and Enterprise Conference, launched in 2018, focused on impact and public engagement, 192 colleagues attended. The Conference returned to this theme in July 2019 and 155 colleagues attended.
3.4 | Evaluation of the Careers Coaching Scheme will be carried out. |  | Human Resources | September 2017 | Achievement of coaching goals (including increased satisfaction with career direction, work life balance and level of confidence following coaching). |  | COMPLETE | Career coach training has taken place and career coaching is available as part of the University's coaching network. Evaluation with coachees found the following longer term benefits - positive career changes, breaking through limiting assumptions that were holding them back, gaining new perspectives and choices. We were shortlisted for a Universities Human Resources (UHR) Award in the Organisational Development and culture change category for our leadership of the Leeds citywide coaching network.
3.5 | Our contribution points and Contribution Reward policy will be reviewed as part of our review of our reward and recognition arrangements. | 2.6 | Human Resources | December 2020 | Development of new options to reward and recognise contribution and success. | People Strategy | ONGOING | As part of the refreshed People Strategy, we are currently auditing our range of reward and recognition mechanisms, which will be informed by our organisational values and priorities alongside broader considerations including changes to the pension schemes and the outcomes of national pay negotiations. We are planning a longer term reward strategy for 2020 onwards.
3.5 | Ensure that career development and promotion opportunities are communicated directly to staff, via their managers, and through our website in addition to staff checking for existing vacancies on our recruitment site. | 2.6 | Deans of School, Directors of Research | December 2020 | Staff feedback at the next focus group indicates greater awareness of development and promotion opportunities. | Athena SWAN 4.3 | ONGOING | The Annual Academic Promotions round is communicated directy to all staff each year through an email from the Vice Chancellor, including publicising dates for open metings about the promotion criteria. The University's job website provides information on all vacancies, including internal opportunities. It is planned to seek colleague feedback on development opportunities via a comprehensive colleague survey in 2020.
3.6 | All new academic staff will log a local induction agreement with HR using the existing guidance as a template and which will also include an initial research plan. |  | Human Resources with Deans of School | September 2018 | 100% of new academic starters have a local induction agreement and research plan. | Athena SWAN 3.3a | COMPLETE | The induction checklist for new starters has been revised in conjunction with Schools and implemented from July 2018. This includes a comprehensive template and monitoring process that is in use for all new academic colleagues, including a log of induction checklist completions within each School. Our Student and Staff Development Unit receives monthly updates from HR on new appointments. All research staff appointments receive a personalised welcome e-mail to all new staff who have a research element to their role. this e-mail introduces the team and key signposting and resources including regulations, policies, processes, training opportunities. Also, specific Researcher Induction which outlines our processes / procedures / expectations / development opportunities. This is supported by our Research Staff Development Programme of ‘whole career’ training with recognised pathways of career development. Positive action statements are used to increase participation in researcher training to advance career development and promote researcher confidence.
3.6 | To survey new staff and line managers to establish how effectively the existing probationary scheme supports induction and career development. |  | Human Resources | December 2020 | Survey completed and actions identified to improve career development. New staff surveys show satisfaction levels with local induction are at 90% or more. | Athena SWAN 3.3b, 4.10 | ONGOING | In April 2018 we added questions to our New Starter Survey linked to probation. 76.9% commented that a probationary period applied to their role (10.3% did not know and 12.8% did not have a probationary period). Of these respondents 44.9% felt that their probationary period helped them to settle in to their role (10.3% disagreed and 44.9% neither agreed nor disagreed). 33.3% discussed career development as part of their probationary period (21.8% disagreed, 42.3% neither agreed nor disagreed and the remainder did not answer the question). In relation to induction, 100% of academic/research colleagues responding agreed that the University was welcoming and 90% felt supported by colleagues. The development of a listening strategy forms one of the refreshed People Strategy priorities.
3.6 | We will introduce an ‘onboarding’ process to ensure that we present an integrated and user-friendly approach to our new people. |  | Human Resources | December 2019 | Positive feedback from new starters regarding onboarding process. The percentage of staff recruited within the last 12 months who have left the University voluntarily to be below 9.3% (DLA Piper HE Benchmark). | People Strategy | ONGOING | The DLA Piper Scorecard provides the percentage of staff recruited within the last 12 months who have left the Leeds Beckett voluntarily compared with the HE sector. On the 2018 Scorecard these percentages were 2.6% for Leeds Beckett, compared with 9.7% for the sector. The onboarding process has been improved through the launch of an onboarding buddy video (and supporting documents for the manager and the buddy), plus more communication during the process.
Principle 4: The importance of researchers’ personal and career development, and lifelong learning, is clearly recognised and promoted at all stages of their career.
4.1 | Ensure that every member of academic staff has an individual research plan as part of the annual PDR process. | 2.3, 3.1 | Directors of Research | May 2019 | All academic staff PDRs to have individual research plans included by 2019. | Athena SWAN 4.2a | ONGOING | To promote and support all academic staff to develop an individual research plan. At University level The Researcher Developer team within the Graduate School circulated the approved Staff Development Programme to Deans and Directors of Research to disseminate accordingly. Schools across the university have introduced ‘Research and Enterprise Coordinator’ role in all academic Subject Groups (all staff across the university are housed within an academic Subject Group at School level). These coordinators work with staff, from ECR to Experienced, to identify research priorities and plans across respective groups. These plans can be used to inform PDR and deployment meetings with Subject Group Leads. The Researcher Development team, supported by our Academic Lead, offer and deliver School specific workshops as appropriate, e.g. School of Built Environment where approximately 26 colleagues attended and School of Education where 11 colleages attended during academic year 2018/19.
4.5 | Directors of Research will own the mentoring scheme for their respective areas supported by the Graduate School with clearly defined success measure linked to the REF. Actively promote the mentoring scheme to female staff, including use of positive action statements, to support career progression. Identify clear criteria by which the revised research mentoring scheme will be evaluated and report on this annually. | 3.7 | Directors of Research | July 2018 | Mentoring scheme promoted via web, networks and local School updates. Numbers of staff, by gender, accessing a mentor included in Annual School/Unit research report. Criteria established (including take-up by female staff) and evaluation included in University research report. | Athena SWAN 4.6a, 4.6b and 4.6c | ONGOING | Schools have autonomy regarding the management and delivery of research and staff mentoring schemes. An example is Carnegie Research Mentoring Scheme which aims to provide collegiate support for staff to develop their research and scholarly activity. The system operates by matching a mentee with a mentor who has relevant research expertise, skills and interests. The mentor's role is to help the mentee achieve certain agreed objectives in order to progress along the research continuum. A further example is evidenced of a formal mentoring scheme in our PysCen mentoring programme which allows academic colleagues to state their needs and identify potential mentors. Various organised events supplement this programme throughout the year, including writing retreats.
Principle 5: Individual researchers share the responsibility for and need to pro-actively engage in their own personal and career development, and lifelong learning.
5.1 | Early career staff and those embarking on research for the first time should have an allocation to reflect the need to develop their research profile and in sufficiently contiguous blocks. |  | Deans of School | July 2019 | Early career researchers have research time allocated in continuous blocks. | Athena SWAN 3.1d | ONGOING | An exceptional example of the University supporting ECRs by allocated time is demonstrated in the work of an extremely inspiring early career researcher, a national and international world leader fashion designer who has been described by the New York Times (NYT) as one of the ‘Names you need to know’ (15/09/17). His contribution to fashion design was formally recognised when he was shortlisted for the ‘British Emerging Womenswear Talent’ at ‘The British Fashion Awards’ (2017 and 2018). his was invited to speak at ‘Fashion’s Future Stars’ at the Victoria & Albert Museum and has been referred to in a full Guardian feature as: “fashion’s great bright hope” (14/02/2018). Promoting the research of this young talented researcher, the Director of Research for the School of Art, Architecture and Design facilitated him representing our University and the City of Leeds in the London Design Biennale 2018, in a collaborative partnership between Leeds Beckett University and Leeds City Council. Sumantro Ghose, the Managing Director for the London Design Biennale said this ECR’s installation at the Biennale was “extraordinary”. An extract of this ECR’s work can be found: https://www.leedsbeckett.ac.uk/news/0918-leeds-takes-centre-stage-at-london-design-biennale-2018/. We also have a rolling two year rotational posts for upto four Senior Lecturers on the University Research Degrees Sub Committee.
5.4 | Provide specific research promotion workshops each year as part of the people development programme aimed at particular points in the promotion 'pipeline' – Becoming a Principal Lecturer, Reader, Reader to Professor, PhD to Postdoc and encourage female academics to attend these. | 2.3, 2.6 | DVC (Research & Enterprise) | September 2018 | Workshops developed and in place. Expectation that 50% of attendees are women. | Athena SWAN 2.3g | ONGOING | During May 2017 we ran 9 sessions, 79 academic colleagues attended, 48 male and 31 female. 23 of those who attended have since become Readers (12 male, 11 female) and 6 Professors (3 male, 3 female - including 4 colleagues who were Readers at the time who are now Professors)
5.5 | Increase the number of female STEM academics attending Leadership/Management development courses e.g. Aurora, Coaching, Mentoring, Leadership Foundation accredited development and the in-house people development programme. | 2.3 | Human Resources | October 2018 | Number of female STEM academics accessing these development activities increases by 25% by October 2018. | Athena SWAN 4.1a | COMPLETE | 4 STEM colleagues completed the Aurora programme in 2017 and 8 female academics in STEM subjects completed in 2018 (for this cohort, STEM academics were particularly targeted). Delegates take part in action learning sets as part of the programme and are offered institutional mentoring. Since 2018, 8 female employees (including 6 academics) have participated in the Regional Cross Institutional action learning for women Programme https://regionalactionlearning.weebly.com/. The aim of the sets is to provide a space to focus on career enhancement and to provide networking opportunities across the HE sector. There have been over 150 attendees on various leadership development sessions targeted at Academic Leaders (mainly Heads of Subject and Course Directors) since September 2017 (approx. 65% of attendees were female).
5.5 | Introduce a more targeted approach to research development clearly signposted for Early Career Researchers, Mid-career, Principal Lecturers etc. Include internal funding awards, research award development (e.g. supervision training/examination and independent chairing). |  | Human Resources and Head of the Graduate School | July 2018 | Targeted approach in place and publicised. Monitoring by gender of internal funding and development opportunities show a gender split of 50% for those accessing these. Data included in annual University research report. | Athena SWAN 4.5c | COMPLETE | The Graduate School facilitated a SLWG to enhance our ECRN in 2017 and we targeted our research staff workshops through marketing campaigns to promote maximum take up by relevant staff, including ECRs. We delivered 47 workshops in 2018/2019 282 academic colleagues attended, 179 females and 103 males. Due to changes in how funding has been distributed within the University the opportunity to run central internal award schemes has been put on hold.
Principle 6: Diversity and equality must be promoted in all aspects of the recruitment and career management of researchers.
6.1 | Development of a five-year Equality and Diversity Framework for the University | 6.3, 6.7 | Human Resources | January 2018 | Framework in place, Equality and Diversity targets and KPIs developed and subject to monitoring and review. | People Strategy | COMPLETE | The Equality, Diversity and Inclusion Framework (Strategy) has been agreed, following wide ranging consultation, and is published on the University's public facing webpages http://www.leedsbeckett.ac.uk/public-information/equality-and-diversity/policy-and-resources/
6.1 | Race Charter working groups to be established to propose and lead on developments and enhancements needed to better support race equality. Race Equality Charter Bronze Award (2016-2019). | 6.3, 6.7 | Human Resources | Submission 2019 | Achievement of Race Equality Charter Bronze Award. |  | ONGOING | Working groups have been established and met to provide an initial draft of the action plan, which was discussed at the REC Steering Group. It is now intended to submit for the Race Equality Charter Bronze Award in 2021.
6.2 | We will bring our staff gender profile in civil engineering and electrical & electronic engineering closer to the national HE average | 1.2, 6.1 | Human Resources | January 2020 | Gender balance moves to within 3% of the national HE average by 2020. | Athena SWAN 2.1 | ONGOING | In the 2014/15 HESA return, Leeds Beckett staff gender balance was Civil engineering (15% female LBU vs 21% national) and Electrical & Electronic engineering (0% female LBU vs 14% national). There are a small number of academic colleagues in these subject areas, and so a small increase or decrease in FTE can lead to a large percentage increase or decrease. For the 2017/18 academic year, Leeds Beckett staff gender balance was Civil Engineering (7% female LBU vs 23% national) and Electrical & Electronic Engineering (17% female LBU vs 14% national). The language of adverts has been reviewed and we are actively using positive action statements and networks as appropriate.
6.4 | There are a number of actions included in the University’s Athena SWAN Action Plan in relation to providing additional support for staff returning from maternity leave, shared parental leave, career breaks, etc, including establishing a support network and reviewing arrangements/ communication for flexible working and return to work. | 6.5, 6.8, 6.9 | Human Resources | October 2018 | Specific measures to support those returning from maternity and shared parental introduced. 100% of maternity/shared parental leave returners confirm that provision is consistent and comprehensive (including risk assessments completed, reintroduction programme in place). Manager Guidance produced, published and in use. Support network is established and publicised on HR webpages and in staff maternity letters. | Athena SWAN 5.1, 5.2, 5.3 | COMPLETE | Human Resources continue to strengthen the support for staff returning to work from maternity leave, shared parental leave, career breaks etc. A new family friendly webpage is available, including a maternity checklist and guidance for managers, relevant policies, and links to the University’s holiday club for children and return to work mentoring scheme. Our Return to Work Mentoring Scheme has 16 mentors available to support colleagues and is publicised on HR webpages and in staff maternity letters. Since January 2017, 20 successful mentoring relationships have been established. Special circumstances (including career breaks) are specifically referenced in the Academic Promotions Policy www.leedsbeckett.ac.uk/public-information/human-resources-guides-and-support/ "For part time members of staff (or those who have had a period of absence such as maternity leave or a career break), whilst there will be no difference in the level of achievement required, special consideration will be given to the volume/range of evidence and any gaps in output" and recruitment and selection training.
6.5 | Promote our existing flexible working practice and benefits on our vacancy website and signpost this in our adverts. | 6.4 | Human Resources | April 2018 | Flexible working practice signposted in 100% of adverts | Athena SWAN 2.2e | COMPLETE | Adverts refer to the wide range of benefits which can be accessed when working at Leeds Beckett, including flexible working. Work is in progress with Corporate Communications colleagues to develop and promote our employer brand.
6.5 | Produce a flexible working leaflet which sets out in one place what staff working at the University are able to access. | 6.4 | Human Resources | April 2018 | Flexible working leaflet produced, publicised and in use. | Athena SWAN 2.2f | COMPLETE | Our new family friendly webpage signposts policies to support parents and carers (Flexible Working Policy, Time off for Public Duties and Special Leave and Parental Leave) and the Carers Network, in addition to policies/support for new parents.
6.1 | Establish an Athena SWAN network to raise awareness of Athena SWAN more widely, provide opportunities for cross institution working and learning and link to the School based Champions and Aurora network. | 6.3, 6.7 | E&D Manager, Senior Aurora Champion | December 2017 | Network in place. Measure staff knowledge of Athena SWAN via surveys. | Athena SWAN 6.1a | COMPLETE | Awareness of Athena SWAN has been raised more widely through the School submissions (3 Schools have submitted for the award and a further 3 have formed School Athena SWAN Steering Groups). Linked to these School submissions, surveys of academic colleagues have taken place, including questions on behaviours, people policies, fairness and career progression.
6.1 | Develop a 3 year Athena SWAN Communications Plan to incorporate all areas of the University and the expanded 2015 Charter principles. | 6.3, 6.7 | Athena SWAN Steering Group | May 2017 | 3 year Athena SWAN Communications Plan in place. | Athena SWAN 6.1b | COMPLETE | In place, to be reviewed annually.
6.1 | We will submit 3 [Athena SWAN] school awards (25% of our schools) by April 2018. Deans of School have committed to submit for a departmental award in their school strategic plans. | 6.3, 6.7 | DVC (Research & Enterprise) | April 2018 | 3 School awards submitted. | Athena SWAN 1.4a | COMPLETE | The School of Clinical and Applied Sciences and the School of Cultural Studies and Humanities submitted (unsuccessfully) for the Athena SWAN School award in April 2018. Leeds School of Social Sciences submitted (unsuccessfully) in November 2018. The School of Events, Tourism and Hospitality Management, School of Film, Music & Performing Arts and School of Art, Architecture and Design have all formed School Athena SWAN Steering Groups. A full review of the University's Athena SWAN action plan is underway for institution resubmission in 2021.
Principle 7: The sector and all stakeholders will undertake regular and collective review of their progress in strengthening the attractiveness and sustainability of research careers in the UK.
7.1 | Human Resources and the Graduate School will co-author an annual progress report on the HR Excellence in Research Action Plan. |  | Human Resources and Graduate School | July 2018 | Annual report shows good progress against action plan. |  | COMPLETE | A review of our actions has taken place. The Graduate School jointly with Human Resources co-authored a report reviewing the progress made which was disseminated through the University's Research and Enterprise Committee in June 2018. This showed good process against the action plan, including the agreement of the Equality, Diversity and Inclusion Framework, strengthened support for parents and others who have taken career breaks, submission for Athena SWAN School Awards, researcher recognition through the inaugural Gender Research Conference and implementation of a new annual process for promotion to Professor and Reader.
7.1 | Progress against the HR Excellence in Research Action Plan will be a regular standing item on the University’s Research and Enterprise Committee agenda (the Committee meets quarterly). |  | Graduate School | Ongoing | Formal record of cross university representation to enhance and capture collective review against the action plan. |  | COMPLETE | We now have a group of Directors of Research who are responsible for the development of research across our University. The engagement and review on progress against the HR Excellence in Research actions will be part of their remit supported by the Graduate School and will be discussed quarterly at their University Research and Enterprise Forum meetings. The Research and Enterprise Committee will receive an annual report on the HR Excellence in Research and will formally approve actions and future submissions.
7.2 | Present the CROS & PIRLS survey results to the Research & Enterprise Committee in October 2017 with an action plan for any gaps identified as a result. | 7.1 | DVC Research & Enterprise, Research Directors & HR | October 2017 | Assess user feedback to strengthen the action plan against key areas. | Concordat Reference C6 C7 C9 | COMPLETE | We sought to dramatically improve uptake of CROS and PIRLS surveys in 2019. A changed methodology, informed by Head of Graduate School and HR and in accordance with VITAE guidelines was used: CROS was distributed to 164 research staff, 6 of those were FTCRs. PIRLS was distributed to 344 research staff, 11 of those were FTCRs. Both surveys were distributed to specific research colleagues as defined by VITAE in the guidance document ‘FAQs’ (downloaded 11/03/2019). Data on staff was obtained from HR in line with VITAE’s guidelines; institutional based, specific development questions were included in both CROS & PIRLS to obtain further views from our staff, including FTCRs. At the point of finalising our HR Excellence in Research Awards submission our response rates were 25% CROS (14/163) and 17% PIRLS (61/344) (as opposed to 0.074% in 2017). Feedback received following CROS & PIRLS was considered by the Graduate School, our Academic Lead and presented at University R&E Committee; it was agreed that a SLWG be established to support FTCRs and ECRs and highlight any specific issues for these staff. FTCRs are encouraged to engage in our Researcher Development programme and can access our online People Development programme. These are highlighted with FTCRs at induction, PDR meetings and via School Research and Enterprise Committees. As ECRs can be FTCRs or FTEs, we have appointed a dedicated Graduate School colleague to facilitate our Early Career Network to assess the specific needs of FTCRs within this group of staff and to feedback to Director of Research and Researcher Development as appropriate. This informs our ongoing action plan. Activities underway include workshops on research funding (with particular emphasis on ECRs) and career development sessions showcased at Research and Enterprise conference on e.g. impact in research, knowledge transfer partnerships.
Note on I15: Bissas, Sarabjit:
Note on I16: Bissas, Sarabjit: Also, how are you recognising the contribution FTCRs have made and their specific needs? Also, does the PDR process allow you to mine the training needs for researchers ie ECRs / FTCRs? if so, have you identified trends to ensure our University wide training is fit for purpose? Also, who can access the leadership programmes - can ECRs?