## Actions for 2019-2021
| HR Excellence In Research Action Plan |  |  |  |  | COMPLETE
Link to Principles and previous HR Excellence in Research submission: http://www.leedsbeckett.ac.uk/research/hr-excellence-in-research-award-for-leeds-beckett/ | [5 empty] | Live - On Schedule
Last Reviewed: 29 April 2020 | [5 empty] | Planned - not started/not due
ACTIONS FOR 2019-21 | [5 empty] | Behind Schedule - low priority
Behind Schedule - high priority
Action number | Action | Responsibility | Deadline | Success Criteria/Outcome Measures | Links to other Strategies/Action plans | Status | Comments
Principle 1: Recognition of the importance of recruiting, selecting and retaining researchers with the highest potential to achieve excellence in research.
1.1 | Require gender-balanced shortlists for all senior academic recruitment where search agencies are used. | Human Resources | December 2020 | Gender balanced shortlists received from search agencies (leading to an increase in the number of women in senior roles). | Gender Pay Gap Report 2018
1.2 | Complete a review to understand the experience of female applicants to research positions, and identify any barriers to applicants. This will include a review of job descriptions and shortlist criteria for terminology or phrasing which may be a barrier. | Human Resources | December 2020 | Review completed and recommendations for action implemented. Longer term aim to increase in the number of female applicants applying for academic (including research) positions to achieve a 50:50 Male/Female balance (in 2018/19 42.21% of applicants for academic positions were female and 46.27% of applicants for research positions were female). | Athena SWAN
1.3 | Ensure shortlisting and interview panels are diverse in composition. | Human Resources | July 2020 | Monitoring of recruitment panel membership in place and analysis/report on a 6 monthly basis. | Gender Pay Gap Report 2019 Race Equality Charter
Principle 2: Researchers are recognised and valued by their employing organisation as an essential part of their organisation’s human resources and a key component of their overall strategy to develop and deliver world-class research.
2.1 | Modernise our approach to performance development to enhance individual and team performance, including increased manager skills for effective performance management conversations. Provide specific guidance so that the research community can engage effectively with the performance development review process | Human Resources | May 2021 | • Objective setting and development plans for those engaged in research linked to our organisational research strategy. • All reviewers have accessed training on good quality performance conversations. • Colleague survey results indicate that the research community have clear objectives and focused development plans • Guidance developed with and for the Research Community published on the intranet. | People Strategy
2.2 | Academic staff (including Researchers) will be actively encouraged by managers to take up promotion opportunities through the annual PDR process. | Deans of School and Heads of Subject | December 2020 | All academic staff (including Researchers) to have discussion of career development and promotion annually as part of the PDR process. | Athena SWAN Race Equality Charter
2.3 | We will review our academic career pathways, including teaching and learning, research and enterprise. We will continue to enhance the use of developmental roles including the use of Graduate Teaching Assistants. We will record and review the career development and progression of our research community. | Human Resources | July 2021 | Clear career pathways in place and supported by published guidance, information and other development resources for colleagues that support career progression . Representation of women within the Professoriate to rise to 35% by 2021. Data shows career development and progression at all levels within the research community. | People Strategy
Principle 3: Researchers are equipped and supported to be adaptable and flexible in an increasingly diverse, mobile, global research environment.
3.1 | Deliver sessions on ‘Research Impact’ and ‘Public Engagement’ once a term, recognising different levels of researcher experience in content. Promote to FTCRs at induction and to ECRs via DoRs, Centre Heads and R & E Coordinators at School level | Graduate School Directors of Research | July 2021 | Increased attendance recorded via i-Trent. Maximum cohorts attending (depending on workshop size) | Staff Development Programme |  | Online resources will be developed to provide greater access to information.
3.2 | Continue to deliver 'PGR Mental Health and Wellbeing' workshop within our Research Awards Supervision (RAS) training day, flag up at Experienced Supervisor workshops and deliver stand-alone workshop twice yearly. | Graduate School | July 2021 | Open lines of communication between staff supervising PGRs, staff acting as PIs and appropriate wellbeing services within the University | Strategic Framework for the Wellbeing and Mental Health of our Colleagues |  | Online resources for staff will be enhanced to ensure easy access.
3.3 | Include support for MRes Students as explicit aspect of RAS training sessions | Graduate School Researcher Development | November 2021 | A 10% increase in MRes completions. | Staff Development Programme
3.4 | Refresh the RiSK training package run by R&E Services on applying for research funding in line with CROS and PIRLS feedback to cover small bid applications through to PI responsibilities as appropriate. | Graduate School R&E Services | December 2021 | 5% increase in applications for external funding | Research & Enterprise Strategy 2016-2021
3.5 | Encourage ECRs to undertake Research Awards Supervision (RAS) training and to submit CV for approval where appropriate | Directors of Research/Postgraduate Research Tutors at School and Unit level | August 2021 | Increase in applications for approval as Advisor and Supervisor (where appropriate) at URDSC | Research & Enterprise Strategy 2016-2021
Principle 4: The importance of researchers’ personal and career development, and lifelong learning, is clearly recognised and promoted at all stages of their career.
4.1 | Support all members of academic staff to indicate individual research plan, appropriate to their role, as part of annual PDR process | Directors of Research / Deans of Schools / Heads of Schools | May 2021 | School level reporting on resources allocated for support for research development across academic staff post PDR annual cycle | People Strategy
4.2 | Increase numbers of academic staff engaged in research mentoring | Directors of Research / Graduate School/HR | May 2021 | 10% increase in staff with mentoring agreement in place | Research & Enterprise Strategy 2016-2021
Principle 5: Individual researchers share the responsibility for and need to pro-actively engage in their own personal and career development, and lifelong learning.
5.1 | Support Early Career Researchers to gain Independent Researcher Status (LBU REF 2021 Code of Practice) | Directors of Research, Heads of Subject and R&E Coordinators | July 2021 | 5% increase in Independent Researcher figures | People Strategy/Research & Enterprise Strategy 2016-2021
5.2 | Provide annual workshops detailing expectations for promotions to senior research roles | DVC (Research & Enterprise) | January 2020 | An increased number of successful women applicants. Representation of women within the Professoriate to rise to 35% by 2021. | People Strategy and Research & Enterprise Strategy 2016-2021
5.3 | Refresh Research Development Programme and signpost for ECRs, Mid-career and PIs where appropriate | Graduate School | December 2020 | Targeted approach in place and publicised. Monitoring of attendance by gender and positive action statements and academic role of attendees | Research & Enterprise Strategy 2016-2021
5.4 | To run a pilot scheme to support five members of staff to obtain the UKCGE Supervisor Recognition. | Graduate School | August 2021 | The pilot scheme will be run over academic year 2020/2021. Success will be for five researchers to obtain recognition. The outcome of the pilot will be reviewed and rolled out.
5.5 | Develop a communication strategy for disseminating and celebrating successful outputs of FTCRs and ECRs | Graduate School / Library | August 2021 | FTCRs and ECRs Symplectic presence. 20% increase in social media use communicating success and recognition. | Staff Development Programme
5.6 | In response to CROS 2019 pilot targeted induction for new FTCRs in line with Concordat revised principles and disseminate materials to ECRs across the University. | Graduate School | January 2021 | Record of meetings and TNAs for FTCRs with Graduate School Staff Researcher Development team
5.7 | Inform all staff registered for Research Awards of refreshed Researcher Development Programme and highlight ECR support. | Graduate School | January 2021 | Engage with at least 10 ECRs / FTCRs to develop a communication plan to develop and deliver career development workshops.
5.8 | Roll out mandatory online training ‘Academic Integrity’ module for all new research staff. | Graduate School | May 2021 | Monitor take up via People Development online. 100% enrolment by new FTCRs
Principle 6: Diversity and equality must be promoted in all aspects of the recruitment and career management of researchers.
6.1 | Race Charter working groups to propose and lead on developments and enhancements needed to better support race equality (diverse academic, and within that, research, community). Full review of the Athena SWAN action plan ready for institution resubmission, including consideration and analysis of our research community profile. | Human Resources | Submission 2021 | Achievement of Race Equality Charter Bronze Award Retention of Athena SWAN Award
6.2 | Monitor the recruitment and selection, and academic promotion process to develop greater understanding of how different applicant groups progress, and identify the different success rates of different groups. Use this data to develop strategies that will enhance progression rates for groups where this is different to the majority group. | Human Resources | December 2021 | Data set developed that identifies sucess rates at application, shortlisting and appointment for different groups. Using data develop strategies, and set specific targets to improve success rates and apply them in specific Schools to improve outcomes. | Athena SWAN Race Equality Charter
6.3 | Embed wellbeing content in mandatory health & safety training and resources for managers (including new managers) to promote good mental health and wellbeing through the effective management of workloads and people. | Human Resources | September 2020 | • All new colleagues to complete mandatory online health & safety training • 600+ unique views of wellbeing staff webpages • During 2019/20, 75 managers to attend a Manager Matters development session which includes consideration of wellbeing (Team Wellbeing session, Being a manager at LBU, Team strengths and Effective team meetings and 1:1s) | Strategic Framework for the Wellbeing and Mental Health of our Colleagues
Principle 7: The sector and all stakeholders will undertake regular and collective review of their progress in strengthening the attractiveness and sustainability of research careers in the UK.
7.1 | Human Resources and the Graduate School/Research and Enterprise Services will report on the progress of the HR Excellence in Research Action Plan within the Annual Research and Enterprise Report. This report will be presented at the October meeting of the University Research and Enterprise Committee and the relevant section and minutes will be available online. | Human Resources and Graduate School/Research and Enterprise Services | 2021-07-01 | Good progress reported against the action plan. | People Strategy
7.2 | Use the CROS & PIRLS survey outcomes, subsequent national surveys as well as the evidence-based outcomes taken from the Senior Lecturers on the Research Degree Sub-Committee to inform researcher development and the Action Plan. | HR/Graduate School/Research and Enterprise Services/Schools | 2021-05-01 | R&E actions from the surveys and the feedback from the RDSC membership scheme informs researcher development support at appropriate levels. The development needs recorded in PDR and deployment meetings. |  | In 2017/18, the Research Degree Sub-Committee implemented a competitive membership scheme, which saw four senior lecturers on a two-year tenue sitting on the committee as part of a development opportunity. This scheme has been successful and remains part of the normal nominee process for membership.
7.3 | A Steering Group with a membership consisting of the Associate Director of HR or nominee, Director of Research and Enterprise or nominee, two colleagues from Research and Enterprise Services, representation from the schools which will include ECRs and Fixed Term academics. This Group will work with other Groups across the University and review the needs and subsequent actions on an annual basis. | HR/Graduate School/Research and Enterprise Services/Schools | 2021-01-01 | The Steering Group formed and serviced jointly by a representative of the Research and Enterprise Services and HR. 70% representation from Schools.